## Table 1
Site | Master Document Number | Title | Bridging Scope
LAR3 | Proj_No-LAR3-AUT-RPT-0001 | LAR3 AMP BPCS Implementation Phase Project Status Report
LAR3 | Proj_No-LAR3-AUT-RPT-0002 | LAR3 AMP BPCS Implementation Phase Site Survey Report | Rev A
LAR3 | Proj_No-LAR3-AUT-SCH-0001 | LAR3 AMP BPCS Implementation Phase Implementation Phase Schedule | Rev A
LAR3 | Proj_No-LAR3-AUT-SPC-0001 | LAR3 AMP BPCS Configuration Project R520 HMI Implementation Specification | Rev B
LAR3 | Proj_No-LAR3-AUT-SPC-0002 | LAR3 AMP BPCS Implementation Phase Design Specification - DCS(C300) Hardware | Rev B
LAR3 | Proj_No-LAR3C-AUT-PLN-0001 | LAR3 AMP BPCS Implementation Phase Testing Plan
LAR3 | Proj_No-LAR3C-AUT-PLN-0002 | LAR3 AMP BPCS Implementation Phase Cutover Plan
LAR3 | Proj_No-LAR3C-AUT-PLN-0003 | LAR3 AMP BPCS Implementation Phase Site Survey Plan | Rev A
LAR3 | Proj_No-LAR3-PMT-MDR-0001 | LAR3 AMP BPCS Implementation Phase Master Document Register | Rev A
LAR3 | Proj_No-LAR3-VTZ-SPC-0001 | LAR3 AMP BPCS Implementation Phase Design Specification - VM Host and Network
LAR3C | Proj_No-LAR3C-AUT-CAL-0100 | LAR3C AMP BPCS Implementation Phase C300 Controller Loading Calculations - Carson | Rev B
LAR3C | Proj_No-LAR3C-AUT-CAL-0101 | LAR3C AMP BPCS Implementation Phase BPCS C300 Heat and Power Calculations - Carson | Rev B
LAR3C | Proj_No-LAR3C-AUT-DWG-0100 | LAR3C AMP BPCS Implementation Phase BPCS Cabinet Layout Sketch (C300) - Carson | Rev B
LAR3C | Proj_No-LAR3C-AUT-FDS-0100 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - General
LAR3C | Proj_No-LAR3C-AUT-FDS-0101 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - 1#REF - Desulfurizer Heater (RW-0025-214.09)
LAR3C | Proj_No-LAR3C-AUT-FDS-0102 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - 1#REF - Heater (RW-0026-214.09)
LAR3C | Proj_No-LAR3C-AUT-FDS-0103 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - 1#REF - Recycle Compressor (RW-0004.087.06)
LAR3C | Proj_No-LAR3C-AUT-FDS-0104 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - 1#REF - Desulfurization Compressor (RW-0005.087.03)
LAR3C | Proj_No-LAR3C-AUT-FDS-0105 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - 1#REF - Common Compressor (RW-0006.087.03)
LAR3C | Proj_No-LAR3C-AUT-FDS-0106 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - 1#REF - Recycle Compressor (RW-0022.087.06)
LAR3C | Proj_No-LAR3C-AUT-FDS-0107 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - FFHDS - Reactor Feed Heater (RW-0048)
LAR3C | Proj_No-LAR3C-AUT-FDS-0108 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - FFHDS - Prism Compressor (RW-0057.087.32)
LAR3C | Proj_No-LAR3C-AUT-FDS-0109 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - LHU- Feed Heater (RW-0028-214.09)
LAR3C | Proj_No-LAR3C-AUT-FDS-0110 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - FCC- Fresh Feed Born Heater (RW-0023)
LAR3C | Proj_No-LAR3C-AUT-FDS-0111 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - FCC- Pignone Compressor (RW-0053.087.06)
LAR3C | Proj_No-LAR3C-AUT-FDS-0112 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - Merox Unit Alarm PLC (44PLC911) | Rev A
LAR3C | Proj_No-LAR3C-AUT-FDS-0113 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - ALKYC- Refrigerant Compressor (RW-0047.087.06)
LAR3C | Proj_No-LAR3C-AUT-FDS-0114 | LAR3C AMP BPCS Implementation Phase Equipment Functional Design Specification - NHDS - Reactor Feed Heater (RW-0053)
LAR3C | Proj_No-LAR3C-AUT-IOA-0100 | LAR3C AMP BPCS Implementation Phase I/O List - Carson | Rev B
LAR3C | Proj_No-LAR3C-AUT-LOG-0131 | LAR3C AMP BPCS Implementation Phase Configuration Log - ALKY_C300_89P
LAR3C | Proj_No-LAR3C-AUT-LOG-0132 | LAR3C AMP BPCS Implementation Phase Configuration Log - ALKY_C300_91P
LAR3C | Proj_No-LAR3C-AUT-LOG-0133 | LAR3C AMP BPCS Implementation Phase Configuration Log - ALKY_C300_93P
LAR3C | Proj_No-LAR3C-AUT-LOG-0134 | LAR3C AMP BPCS Implementation Phase Configuration Log - ALKY_C300_95P
LAR3C | Proj_No-LAR3C-AUT-LOG-0136 | LAR3C AMP BPCS Implementation Phase Configuration Log - Alky Console
LAR3C | Proj_No-LAR3C-AUT-LOG-0137 | LAR3C AMP BPCS Implementation Phase Configuration Log - 1 Crude Console
LAR3C | Proj_No-LAR3C-AUT-LOG-0138 | LAR3C AMP BPCS Implementation Phase Configuration Log - SRU Console
LAR3C | Proj_No-LAR3C-AUT-LOG-0139 | LAR3C AMP BPCS Implementation Phase Configuration Log - 2 Crude Console
LAR3C | Proj_No-LAR3C-AUT-LOG-0140 | LAR3C AMP BPCS Implementation Phase Configuration Log - ISOM
LAR3C | Proj_No-LAR3C-AUT-LST-0100 | LAR3C AMP BPCS Implementation Phase 3rd Party Interface List - Carson
LAR3C | Proj_No-LAR3C-AUT-LST-0101 | LAR3C AMP BPCS Implementation Phase Serial IO List - South Area CEMS Data Concentrator (31PLC-9036)
LAR3C | Proj_No-LAR3C-AUT-LST-0102 | LAR3C AMP BPCS Implementation Phase Serial IO List - South Area CEMS Data Concentrator (31PLC-xxxx)
LAR3C | Proj_No-LAR3C-AUT-LST-0106 | LAR3C AMP BPCS Implementation Phase Serial IO List - Alky Ref Compressor (CCC Controllers)
LAR3C | Proj_No-LAR3C-AUT-LST-0109 | LAR3C AMP BPCS Implementation Phase Serial IO List - Butamer Dryer PLC AB (82-LCP-07)
LAR3C | Proj_No-LAR3C-AUT-LST-0110 | LAR3C AMP BPCS Implementation Phase Serial IO List - TRS Process Analyzer (68AT-912)
LAR3C | Proj_No-LAR3C-AUT-LST-0121 | LAR3C AMP BPCS Implementation Phase Migration PI Tag List - Carson
LAR3C | Proj_No-LAR3C-AUT-LST-0122 | LAR3C AMP BPCS Implementation Phase Migration MAPV Tag List - Carson
LAR3C | Proj_No-LAR3C-AUT-PRO-0100 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - ALKY_C300_89P
LAR3C | Proj_No-LAR3C-AUT-PRO-0101 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - ALKY_C300_91P
LAR3C | Proj_No-LAR3C-AUT-PRO-0102 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - ALKY_C300_93P
LAR3C | Proj_No-LAR3C-AUT-PRO-0103 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - ALKY_C300_95P
LAR3C | Proj_No-LAR3C-AUT-PRO-0104 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - ALKY
LAR3C | Proj_No-LAR3C-AUT-PRO-0105 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - 1 CRUDE
LAR3C | Proj_No-LAR3C-AUT-PRO-0106 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - SRU
LAR3C | Proj_No-LAR3C-AUT-PRO-0107 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - General
LAR3C | Proj_No-LAR3C-AUT-PRO-0108 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - 1#REF - Desulfurizer Heater (RW-0025-214.09)
LAR3C | Proj_No-LAR3C-AUT-PRO-0109 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - 1#REF - Heater (RW-0026-214.09)
LAR3C | Proj_No-LAR3C-AUT-PRO-0110 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - 1#REF - Recycle Compressor (RW-0004.087.06)
LAR3C | Proj_No-LAR3C-AUT-PRO-0111 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - 1#REF - Desulfurization Compressor (RW-0005.087.03)
LAR3C | Proj_No-LAR3C-AUT-PRO-0112 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - 1#REF - Common Compressor (RW-0006.087.03)
LAR3C | Proj_No-LAR3C-AUT-PRO-0113 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - 1#REF - Recycle Compressor (RW-0022.087.06)
LAR3C | Proj_No-LAR3C-AUT-PRO-0114 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - FFHDS - Reactor Feed Heater (RW-0048)
LAR3C | Proj_No-LAR3C-AUT-PRO-0115 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - FFHDS - Prism Compressor (RW-0057.087.32)
LAR3C | Proj_No-LAR3C-AUT-PRO-0116 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - LHU- Feed Heater (RW-0028-214.09)
LAR3C | Proj_No-LAR3C-AUT-PRO-0117 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - FCC- Fresh Feed Born Heater (RW-0023)
LAR3C | Proj_No-LAR3C-AUT-PRO-0118 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - FCC- Pignone Compressor (RW-0053.087.06)
LAR3C | Proj_No-LAR3C-AUT-PRO-0119 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - Merox Unit Alarm PLC (44PLC911)
LAR3C | Proj_No-LAR3C-AUT-PRO-0120 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - ALKYC- Refrigerant Compressor (RW-0047.087.06)
LAR3C | Proj_No-LAR3C-AUT-PRO-0121 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - NHDS - Reactor Feed Heater (RW-0053)
LAR3C | Proj_No-LAR3C-AUT-PRO-0123 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - South Area CEMS Data Concentrator (31PLC-9036)
LAR3C | Proj_No-LAR3C-AUT-PRO-0124 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - South Area CEMS Data Concentrator (31PLC-xxxx)
LAR3C | Proj_No-LAR3C-AUT-PRO-0128 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - Alky Ref Compressor (CCC Controllers)
LAR3C | Proj_No-LAR3C-AUT-PRO-0130 | LAR3C AMP BPCS Implementation Phase SAT Procedure - Carson
LAR3C | Proj_No-LAR3C-AUT-PRO-0131 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - Butamer Dryer PLC AB (82-LCP-07)
LAR3C | Proj_No-LAR3C-AUT-PRO-0131 | LAR3C AMP BPCS Implementation Phase SIT Procedure - Carson
LAR3C | Proj_No-LAR3C-AUT-PRO-0132 | LAR3C AMP BPCS Implementation Phase C-FAT Procedure - TRS Process Analyzer (68AT-912)
LAR3C | Proj_No-LAR3C-AUT-PRO-0133 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - 2 CRUDE
LAR3C | Proj_No-LAR3C-AUT-PRO-0134 | LAR3C AMP BPCS Configuration Project C-FAT Procedure - ISOM
LAR3C | Proj_No-LAR3C-AUT-PRO-0150 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - 1#REF - Desulfurizer Heater (RW-0025-214.09)
LAR3C | Proj_No-LAR3C-AUT-PRO-0151 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - 1#REF - Heater (RW-0026-214.09)
LAR3C | Proj_No-LAR3C-AUT-PRO-0152 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - 1#REF - Recycle Compressor (RW-0004.087.06)
LAR3C | Proj_No-LAR3C-AUT-PRO-0153 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - 1#REF - Desulfurization Compressor (RW-0005.087.03)
LAR3C | Proj_No-LAR3C-AUT-PRO-0154 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - 1#REF - Common Compressor (RW-0006.087.03)
LAR3C | Proj_No-LAR3C-AUT-PRO-0155 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - 1#REF - Recycle Compressor (RW-0022.087.06)
LAR3C | Proj_No-LAR3C-AUT-PRO-0156 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - FFHDS - Reactor Feed Heater (RW-0048)
LAR3C | Proj_No-LAR3C-AUT-PRO-0157 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - FFHDS - Prism Compressor (RW-0057.087.32)
LAR3C | Proj_No-LAR3C-AUT-PRO-0158 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - LHU- Feed Heater (RW-0028-214.09)
LAR3C | Proj_No-LAR3C-AUT-PRO-0159 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - FCC- Fresh Feed Born Heater (RW-0023)
LAR3C | Proj_No-LAR3C-AUT-PRO-0160 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - FCC- Pignone Compressor (RW-0053.087.06)
LAR3C | Proj_No-LAR3C-AUT-PRO-0161 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - Merox Unit Alarm PLC (44PLC911)
LAR3C | Proj_No-LAR3C-AUT-PRO-0162 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - ALKYC- Refrigerant Compressor (RW-0047.087.06)
LAR3C | Proj_No-LAR3C-AUT-PRO-0163 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - NHDS - Reactor Feed Heater (RW-0053)
LAR3C | Proj_No-LAR3C-AUT-PRO-0169 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - Alky Ref Compressor (CCC Controllers)
LAR3C | Proj_No-LAR3C-AUT-PRO-0172 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - Butamer Dryer PLC AB (82-LCP-07)
LAR3C | Proj_No-LAR3C-AUT-PRO-0173 | LAR3C AMP BPCS Implementation Phase i-FAT Procedure - TRS Process Analyzer (68AT-912)
LAR3C | Proj_No-LAR3C-AUT-RPT-0113 | LAR3C AMP BPCS Configuration Project Test Report - ALKY_C300_89P
LAR3C | Proj_No-LAR3C-AUT-RPT-0114 | LAR3C AMP BPCS Configuration Project Test Report - ALKY_C300_91P
LAR3C | Proj_No-LAR3C-AUT-RPT-0115 | LAR3C AMP BPCS Configuration Project Test Report - ALKY_C300_93P
LAR3C | Proj_No-LAR3C-AUT-RPT-0116 | LAR3C AMP BPCS Configuration Project Test Report - ALKY_C300_95P
LAR3C | Proj_No-LAR3C-AUT-RPT-0117 | LAR3C AMP BPCS Configuration Project Test Report - ALKY
LAR3C | Proj_No-LAR3C-AUT-RPT-0118 | LAR3C AMP BPCS Configuration Project Test Report - 1 CRUDE
LAR3C | Proj_No-LAR3C-AUT-RPT-0119 | LAR3C AMP BPCS Configuration Project Test Report - SRU
LAR3C | Proj_No-LAR3C-AUT-RPT-0119 | LAR3C AMP BPCS Configuration Project Test Report - 2 CRUDE
LAR3C | Proj_No-LAR3C-AUT-RPT-0119 | LAR3C AMP BPCS Configuration Project Test Report - ISOM
LAR3C | Proj_No-LAR3C-AUT-RPT-0120 | LAR3C AMP BPCS Implementation Phase Test Report - General
LAR3C | Proj_No-LAR3C-AUT-RPT-0121 | LAR3C AMP BPCS Implementation Phase Test Report - 1#REF - Desulfurizer Heater (RW-0025-214.09)
LAR3C | Proj_No-LAR3C-AUT-RPT-0122 | LAR3C AMP BPCS Implementation Phase Modpack Gap Analysis - Carson
LAR3C | Proj_No-LAR3C-AUT-RPT-0122 | LAR3C AMP BPCS Implementation Phase Test Report - 1#REF - Heater (RW-0026-214.09)
LAR3C | Proj_No-LAR3C-AUT-RPT-0123 | LAR3C AMP BPCS Implementation Phase Test Report - 1#REF - Recycle Compressor (RW-0004.087.06)
LAR3C | Proj_No-LAR3C-AUT-RPT-0124 | LAR3C AMP BPCS Implementation Phase Test Report - 1#REF - Desulfurization Compressor (RW-0005.087.03)
LAR3C | Proj_No-LAR3C-AUT-RPT-0125 | LAR3C AMP BPCS Implementation Phase Test Report - 1#REF - Common Compressor (RW-0006.087.03)
LAR3C | Proj_No-LAR3C-AUT-RPT-0126 | LAR3C AMP BPCS Implementation Phase Test Report - 1#REF - Recycle Compressor (RW-0022.087.06)
LAR3C | Proj_No-LAR3C-AUT-RPT-0127 | LAR3C AMP BPCS Implementation Phase Test Report - FFHDS - Reactor Feed Heater (RW-0048)
LAR3C | Proj_No-LAR3C-AUT-RPT-0128 | LAR3C AMP BPCS Implementation Phase Test Report - FFHDS - Prism Compressor (RW-0057.087.32)
LAR3C | Proj_No-LAR3C-AUT-RPT-0129 | LAR3C AMP BPCS Implementation Phase Test Report - LHU- Feed Heater (RW-0028-214.09)
LAR3C | Proj_No-LAR3C-AUT-RPT-0130 | LAR3C AMP BPCS Implementation Phase Test Report - FCC- Fresh Feed Born Heater (RW-0023)
LAR3C | Proj_No-LAR3C-AUT-RPT-0131 | LAR3C AMP BPCS Implementation Phase Parameter Validation Report - ALKY_C300_89P
LAR3C | Proj_No-LAR3C-AUT-RPT-0131 | LAR3C AMP BPCS Implementation Phase Test Report - FCC- Pignone Compressor (RW-0053.087.06)
LAR3C | Proj_No-LAR3C-AUT-RPT-0132 | LAR3C AMP BPCS Implementation Phase Parameter Validation Report - ALKY_C300_91P
LAR3C | Proj_No-LAR3C-AUT-RPT-0132 | LAR3C AMP BPCS Implementation Phase Test Report - Merox Unit Alarm PLC (44PLC911)
LAR3C | Proj_No-LAR3C-AUT-RPT-0133 | LAR3C AMP BPCS Implementation Phase Parameter Validation Report - ALKY_C300_93P
LAR3C | Proj_No-LAR3C-AUT-RPT-0133 | LAR3C AMP BPCS Implementation Phase Test Report - ALKYC- Refrigerant Compressor (RW-0047.087.06)
LAR3C | Proj_No-LAR3C-AUT-RPT-0134 | LAR3C AMP BPCS Implementation Phase Parameter Validation Report - ALKY_C300_95P
LAR3C | Proj_No-LAR3C-AUT-RPT-0134 | LAR3C AMP BPCS Implementation Phase Test Report - NHDS - Reactor Feed Heater (RW-0053)
LAR3C | Proj_No-LAR3C-AUT-RPT-0136 | LAR3C AMP BPCS Implementation Phase Test Report - South Area CEMS Data Concentrator (31PLC-9036)
LAR3C | Proj_No-LAR3C-AUT-RPT-0137 | LAR3C AMP BPCS Implementation Phase Test Report - South Area CEMS Data Concentrator (31PLC-xxxx)
LAR3C | Proj_No-LAR3C-AUT-RPT-0141 | LAR3C AMP BPCS Implementation Phase Test Report - Alky Ref Compressor (CCC Controllers)
LAR3C | Proj_No-LAR3C-AUT-RPT-0144 | LAR3C AMP BPCS Implementation Phase Test Report - Butamer Dryer PLC AB (82-LCP-07)
LAR3C | Proj_No-LAR3C-AUT-RPT-0145 | LAR3C AMP BPCS Implementation Phase Test Report - TRS Process Analyzer (68AT-912)
LAR3C | Proj_No-LAR3C-AUT-RPT-0151 | LAR3C AMP BPCS Implementation Phase System Migration Impact Assessment Report - Carson | Rev B
LAR3C | Proj_No-LAR3C-AUT-SPC-0101 | LAR3C AMP BPCS Implementation Phase HMI Migration Specification - 1CRUDE | Rev A
LAR3C | Proj_No-LAR3C-AUT-SPC-0102 | LAR3C AMP BPCS Implementation Phase HMI Migration Specification - ALKY-C | Rev A
LAR3C | Proj_No-LAR3C-AUT-SPC-0103 | LAR3C AMP BPCS Implementation Phase HMI Migration Specification - SRU | Rev A
LAR3C | Proj_No-LAR3C-AUT-SPC-0104 | LAR3C AMP BPCS Implementation Phase HMI Migration Specification - 2CRUDE | Rev A
LAR3C | Proj_No-LAR3C-AUT-SPC-0104 | LAR3C AMP BPCS Implementation Phase Console Migration Specification - 1CRUDE, ALKY-C and SRU, 2CRUDE, ISOM
LAR3C | Proj_No-LAR3C-AUT-SPC-0105 | LAR3C AMP BPCS Implementation Phase HMI Migration Specification - ISOM | Rev A
LAR3C | Proj_No-LAR3C-AUT-SPC-0131 | LAR3C AMP BPCS Implementation Phase Software Migration Specification - ALKY_C300_89P
LAR3C | Proj_No-LAR3C-AUT-SPC-0132 | LAR3C AMP BPCS Implementation Phase Software Migration Specification - ALKY_C300_91P
LAR3C | Proj_No-LAR3C-AUT-SPC-0133 | LAR3C AMP BPCS Implementation Phase Software Migration Specification - ALKY_C300_93P
LAR3C | Proj_No-LAR3C-AUT-SPC-0134 | LAR3C AMP BPCS Implementation Phase Software Migration Specification - ALKY_C300_95P
LAR3C | Proj_No-LAR3C-MNL-SPC-0101 | LAR3C AMP BPCS Configuration Project Training Manual 1CRUDE, 2CRUDE, Alky, ISOM, SRU
LAR3C | Proj_No-LAR3C-VTZ-CAL-0100 | LAR3C AMP BPCS Implementation Phase BPCS Network Heat and Power Calculations - Carson | Rev B
LAR3C | Proj_No-LAR3C-VTZ-DWG-0100 | LAR3C AMP BPCS Implementation Phase VM Host and Network Cabinet Layout Sketch - Carson | Rev B
LAR3W | Proj_No-LAR3W-AUT-FDS-0101 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HGU2 - Steam Methane Reformer Heater (H-42) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0102 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HGU2 - Auxillary Boiler (H-43) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0103 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HGU2 - Feed Gas Compressor A (C-146) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0104 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HGU2 - Feed Gas Compressor B (C-147) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0105 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HGU2 - H2 Product Compressor (C-148) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0106 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HGU2 - Hydrogen Compressor (C-84) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0107 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HCU - Recycle Gas Compressor (C-93) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0108 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HCU - Reactor No. 1 H2 Heater (H-300) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0109 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HCU - Reactor No. 2 H2 Heater (H-301) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0110 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HCU - Reactor No. 3 H2 Heater (H-302) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0111 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HCU - 2nd stage charge heater (H-303) | Rev A
LAR3W | Proj_No-LAR3W-AUT-FDS-0112 | LAR3W AMP BPCS Implementation Phase Equipment Functional Design Specification - HCU - Fractionator Reboiler Heater (H-304) | Rev A
LAR3W | Proj_No-LAR3W-AUT-PRO-0001 | LAR3W AMP BPCS Implementation Phase Test Procedure - HGU2 - Steam Methane Reformer Heater (H-42)
LAR3W | Proj_No-LAR3W-AUT-PRO-0002 | LAR3W AMP BPCS Implementation Phase Test Procedure - HGU2 - Auxillary Boiler (H-43)
LAR3W | Proj_No-LAR3W-AUT-PRO-0003 | LAR3W AMP BPCS Implementation Phase Test Procedure - HGU2 - Feed Gas Compressor A (C-146)
LAR3W | Proj_No-LAR3W-AUT-PRO-0004 | LAR3W AMP BPCS Implementation Phase Test Procedure - HGU2 - Feed Gas Compressor B (C-147)
LAR3W | Proj_No-LAR3W-AUT-PRO-0005 | LAR3W AMP BPCS Implementation Phase Test Procedure - HGU2 - H2 Product Compressor (C-148)
LAR3W | Proj_No-LAR3W-AUT-PRO-0006 | LAR3W AMP BPCS Implementation Phase Test Procedure - HGU2 - Hydrogen Compressor (C-84)
LAR3W | Proj_No-LAR3W-AUT-PRO-0007 | LAR3W AMP BPCS Implementation Phase Test Procedure - HCU - Recycle Gas Compressor (C-93)
LAR3W | Proj_No-LAR3W-AUT-PRO-0008 | LAR3W AMP BPCS Implementation Phase Test Procedure - HCU - Reactor No. 1 H2 Heater (H-300)
LAR3W | Proj_No-LAR3W-AUT-PRO-0009 | LAR3W AMP BPCS Implementation Phase Test Procedure - HCU - Reactor No. 2 H2 Heater (H-301)
LAR3W | Proj_No-LAR3W-AUT-PRO-0010 | LAR3W AMP BPCS Implementation Phase Test Procedure - HCU - Reactor No. 3 H2 Heater (H-302)
LAR3W | Proj_No-LAR3W-AUT-PRO-0011 | LAR3W AMP BPCS Implementation Phase Test Procedure - HCU - 2nd stage charge heater (H-303)
LAR3W | Proj_No-LAR3W-AUT-PRO-0012 | LAR3W AMP BPCS Implementation Phase Test Procedure - HCU - Fractionator Reboiler Heater (H-304)
LAR3W | Proj_No-LAR3W-AUT-RPT-0001 | LAR3W AMP BPCS Implementation Phase Test Report - HGU2 - Steam Methane Reformer Heater (H-42)
LAR3W | Proj_No-LAR3W-AUT-RPT-0002 | LAR3W AMP BPCS Implementation Phase Test Report - HGU2 - Auxillary Boiler (H-43)
LAR3W | Proj_No-LAR3W-AUT-RPT-0003 | LAR3W AMP BPCS Implementation Phase Test Report - HGU2 - Feed Gas Compressor A (C-146)
LAR3W | Proj_No-LAR3W-AUT-RPT-0004 | LAR3W AMP BPCS Implementation Phase Test Report - HGU2 - Feed Gas Compressor B (C-147)
LAR3W | Proj_No-LAR3W-AUT-RPT-0005 | LAR3W AMP BPCS Implementation Phase Test Report - HGU2 - H2 Product Compressor (C-148)
LAR3W | Proj_No-LAR3W-AUT-RPT-0006 | LAR3W AMP BPCS Implementation Phase Test Report - HGU2 - Hydrogen Compressor (C-84)
LAR3W | Proj_No-LAR3W-AUT-RPT-0007 | LAR3W AMP BPCS Implementation Phase Test Report - HCU - Recycle Gas Compressor (C-93)
LAR3W | Proj_No-LAR3W-AUT-RPT-0008 | LAR3W AMP BPCS Implementation Phase Test Report - HCU - Reactor No. 1 H2 Heater (H-300)
LAR3W | Proj_No-LAR3W-AUT-RPT-0009 | LAR3W AMP BPCS Implementation Phase Test Report - HCU - Reactor No. 2 H2 Heater (H-301)
LAR3W | Proj_No-LAR3W-AUT-RPT-0010 | LAR3W AMP BPCS Implementation Phase Test Report - HCU - Reactor No. 3 H2 Heater (H-302)
LAR3W | Proj_No-LAR3W-AUT-RPT-0011 | LAR3W AMP BPCS Implementation Phase Test Report - HCU - 2nd stage charge heater (H-303)
LAR3W | Proj_No-LAR3W-AUT-RPT-0012 | LAR3W AMP BPCS Implementation Phase Test Report - HCU - Fractionator Reboiler Heater (H-304)
LAR3W | Proj_No-LAR3W-AUT-RPT-0120 | LAR3C AMP BPCS Implementation Phase System Migration Impact Assessment Report - Wilmington | Rev B
LAR3W | Proj_No-LAR3W-AUT-SPC-0101 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HGU2 - Steam Methane Reformer Heater (H-42)
LAR3W | Proj_No-LAR3W-AUT-SPC-0102 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HGU2 - Auxillary Boiler (H-43)
LAR3W | Proj_No-LAR3W-AUT-SPC-0103 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HGU2 - Feed Gas Compressor A (C-146)
LAR3W | Proj_No-LAR3W-AUT-SPC-0104 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HGU2 - Feed Gas Compressor B (C-147)
LAR3W | Proj_No-LAR3W-AUT-SPC-0105 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HGU2 - H2 Product Compressor (C-148)
LAR3W | Proj_No-LAR3W-AUT-SPC-0106 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HGU2 - Hydrogen Compressor (C-84)
LAR3W | Proj_No-LAR3W-AUT-SPC-0107 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HCU - Recycle Gas Compressor (C-93)
LAR3W | Proj_No-LAR3W-AUT-SPC-0108 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HCU - Reactor No. 1 H2 Heater (H-300)
LAR3W | Proj_No-LAR3W-AUT-SPC-0109 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HCU - Reactor No. 2 H2 Heater (H-301)
LAR3W | Proj_No-LAR3W-AUT-SPC-0110 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HCU - Reactor No. 3 H2 Heater (H-302)
LAR3W | Proj_No-LAR3W-AUT-SPC-0111 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HCU - 2nd stage charge heater (H-303)
LAR3W | Proj_No-LAR3W-AUT-SPC-0112 | LAR3W AMP BPCS Implementation Phase Mod Pack Specification - HCU - Fractionator Reboiler Heater (H-304)